## Read Me
Launch & Cold-Start Planner
Plan a 13-week, constraint-first marketplace evidence cycle.
How to use
Start by identifying the binding constraint: supply, demand, one-sided utility, trust, regulation, or operations. Adapt each threshold to your marketplace model, and record its denominator, observation window, evidence source, owner, and decision. This workbook is educational and is not legal, tax, security, or financial advice.
Directorism
We build custom marketplaces and directories for founders who need strategic clarity and production execution.
Cold Start Score
Score each signal from 0 to 3: 0 = no evidence; 1 = anecdotal or one-off; 2 = repeated but incomplete; 3 = repeated and decision-ready.
Decision bands: 0-6 PAUSE and diagnose the binding constraint; 7-12 IMPROVE the weakest workflow; 13-18 BUILD only the next gated test.
These bands are an internal planning rubric, not an external performance benchmark or an outcome guarantee.

## 13 Week Plan
Week | Supply Goal | Demand Goal | Proof Point | Owner | Status
1 | Define ICP and supply criteria | Define buyer segment | One-page wedge hypothesis
2 | Build first 100 supply target list | Draft demand landing page | Outreach scripts approved
3 | Start supply outreach | Run buyer interviews | First qualified supply responses
4 | Onboard first 10 qualified providers/listings | Collect waitlist or buyer requests | Manual match test
5 | Improve provider profiles | Publish comparison/content page | First conversion signal
6 | Tighten trust/verification | Run first channel test | Activation rate baseline
7 | Expand supply niche | Retarget or follow up demand | Repeatable acquisition channel
8 | Measure liquidity | Measure buyer intent | Supply-demand gap known
9 | Fix onboarding bottleneck | Improve demand CTA | Second conversion test
10 | Add operating process | Launch focused campaign | Weekly operating rhythm
11 | Decide build scope | Decide next channel | MVP scope evidence
12 | Review supply-side evidence | Review demand-side evidence | Draft build / improve / pause decision
13 | Systematize proven supply process | Systematize proven demand process | Confirm build / improve / pause decision

## Cold Start Score
Signal | Threshold / evidence | Actual observation | Score 0-3 | Source / assumption / notes
Qualified supply response rate | Founder-defined rate threshold with denominator and observation window |  |  | Record source, date, window, owner, and whether this is observed or assumed
Supply activation | Required profile/data fields and activation window |  |  | Record source, date, window, owner, and whether this is observed or assumed
Buyer interview urgency | Current workaround, urgency, and budget/time pain |  |  | Record source, date, window, owner, and whether this is observed or assumed
Search or channel intent | Named query, community, partner, or owned channel |  |  | Record source, date, window, owner, and whether this is observed or assumed
Manual match success | Completed or seriously requested manual match |  |  | Record source, date, window, owner, and whether this is observed or assumed
Trust clarity | Documented verification, review, and dispute needs |  |  | Record source, date, window, owner, and whether this is observed or assumed
Total | 0-18 |  |  | Planning rubric, not an external performance benchmark
Decision | BUILD / IMPROVE / PAUSE
Score | Meaning | Evidence standard
0 | No evidence | No observed signal yet
1 | Anecdotal | One-off or unverified signal
2 | Repeated | Repeated signal, but incomplete or not decision-ready
3 | Decision-ready | Repeated, sourced evidence with a named decision
Decision band | Interpretation
PAUSE (0-6) | Insufficient repeated evidence; diagnose the binding constraint
IMPROVE (7-12) | Some repeated evidence; improve the weakest workflow
BUILD (13-18) | Repeated decision-ready evidence; build only the next gated test

## Outreach Tracker
Name | Segment | Channel | Message Angle | Response | Qualified? | Next Step